## T1
Vendor's Mold/Part Issues List
Template Rev01
Part Name |  |  |  |  | XX-XXX |  | 3D IMAGE
OPN with 2D/3D Rev |  |  |  |  | 01
# | ENTRY DATE | TRIAL DATE | TOOL STATUS | ISSUE | SPEC | CAV # | IMAGES | ROOT CAUSES | ACTIONS | CP | DRI |  | REMARKS
[11 empty] | VENDOR | CUSTOMER
1 | 2026-02-03 | 2026-02-05 | OK | ISSUE | SPEC | 1 |  | TEST root cause: ejector pin height slightly proud after maintenance reset. | TEST action: re-match ejector pin height, reduce local push force, and confirm after mold tuning. | TEST 1st article + visual audit | TEST_Tooling_02 | TEST_PD_01 | TEST: mark visible under angled light only.
2 | 2026-02-03 | 2026-02-05 | OK | ISSUE | SPEC | 1 |  | TEST root cause: local packing pressure not fully compensating thick-to-thin transition around rib feature. | TEST action: optimize hold pressure/time and review gate freeze profile on next trial. | TEST section cut review | TEST_Process_03 | TEST_ME_01 | TEST: appearance risk moderate, function unaffected.
3 | 2026-02-03 | 2026-02-05 | OK | ISSUE | SPEC | 1 |  | TEST root cause: corner flow resistance high at current injection speed; fill margin too narrow. | TEST action: increase fill speed window, raise melt temp slightly, and run confirmation at 3 settings. | TEST dimension + fit check | TEST_Mold_PE_01 | TEST_ME_01 | TEST: defect is localized to one cavity / one condition.
4 | 2026-02-03 | 2026-02-05 | OK | ISSUE | SPEC | 1 |  | TEST root cause: melt front hesitation caused by local temperature drop near gate-to-wall transition. | TEST action: tune barrel profile and mold temp balance, then compare A/B samples. | TEST visual panel review | TEST_Process_03 | TEST_PD_02 | TEST: cosmetic issue only, 影像栏位留空 for now.

## Revision History
Rev History | Description | Remark
Rev01 | Initial release | For vendor reference